## Slide 1
EPAC ISTAC
Commissioning plan for 2024-25
Cristina Hernandez-Gomez
May 2024
Notes: The abstract pattern can be removed or repositioned if required. Be careful to ‘Send to Back’ so that it does not obscure any important information.

## Slide 2
Overview
Commissioning activities
Commissioning activities in the laser started in September 23
Requires coordination with ongoing installation tasks
Hold weekly meetings to assess progress and coordinate with some installation tasks
There has been delays with key laser systems : Diode pumps for 100 J amplifier and the front end ns OPCPA pump, both expected to have SAT upcoming weeks
There is a partition wall installed between the compressor are and Ti:Sa amplifier area to separate commissioning and installation activities
The gratings will be delayed so expecting to commissioning parts of beam transport ahead of compressor
Looking a coordination of commissioning activities and installation in the experimental areas in the coming months

## Slide 3
EPAC specification
1PW@10Hz
Output Energy 20 J day 1
Pulse duration ≤ 30 fs FWHM
Repetition rate 10 Hz, 1 Hz, Shot on Demand
Different energy modes available
EPAC Front End-Seed
DPPLS Pump
Green conversion
Ti:Sa High Energy Amplifier
Compressor & diagnostics
Beam transport
2 W Conversion
Compressor
10 Hz TiSa Amplifier
EPAC pump
EPAC seed
Beam propagation
Experimental Areas
EPAC

## Slide 4
Commission single PUMP operating at two repetition rates 1Hz and 10 Hz . Energy will ramp up to a maximum of 120J . Beam will be directed to Ti:Sa amplifier beam transport
Beam will be ready to inject to Ti:Sa room using alignment mode prior to full energy commissioning
Commissioning activities started in September 23 with front end
Pump
10 J Cryo amplifier
Pump Front end
Beam transport
100J Cryo amplifier
Feb 25
May 24
June
July
August
October
September
November
December
Jan 25
CW alignment
10 Hz Commissioning
1 Hz Pulse commissioning
Pump Laser system operational

## Slide 5
Commission the front end subsystems to meet the bandwidth and energy specifications, the different energy modes will be commissioned
Use a temporary stretcher to stretch the pulse to the nanosecond regime for initial commissioning, will require further commissioning of the system with final stretcher
Beam will be ready to inject to Ti:Sa room using alignment mode prior to full commissioning
Commissioning activities started in 2023
Front End
Feb 25
May 24
June
July
August
October
September
November
December
Jan 25
Ps OPCPA1 pulse commissioning
Full energy system Commissioning
CW alignment Ns OPCPA 2
Front End system operational
Ps OPCPA1
Seed
Stretcher
NS OPCPA2
Pump 1
Pump 2
Beam transport
Ns OPCPA2 pulse commissioning
Temporary stretcher pulse commissioning
Final stretcher pulse commissioning

## Slide 6
Feb 25
June 24
July
August
October
September
November
December
Jan 25
Ti:Sa Amplifier operational
CW alignment of amplifier
Full energy system 10Hz
Front End pulse injection
PUMP Injection to 2w
EPAC pump
Front End
High energy Ti:Sa amplifier
2 w conversion and beam shaping
Beam expander and transport
March 25
1Hz pulse commissioning
Ti:Sa Amplifier
Commission Ti:Sa will start in June 24
Commissioning will be coordinated with commissioning activities of PUMP and Front End

## Slide 7
Gold gratings arrive at the end of March 25, the plan has been adjusted
Input expanding telescope is expected later than anticipated
Need to remove the temporary wall between Ti:Sa and compressor for final commissioning
Aug 25
Jan 25
Feb 25
May 25
March 25
April 25
June 25
July 25
Initial CW pencil beam alignment compressor
Pulse system commissioning
CW alignment Final
Compressor operational
Dec 24
Sept 25
CW alignment of Diagnostics
TiS amplifier
Short pulse diagnostics
Compressor
Beam transport
Pulse Compressor
Input VSF alignment

## Slide 8
Oct 25
Feb 25
March 25
April 25
July 25
May 25
June 25
Aug 25
Sept 25
CW alignment beam transport
Pointing tests
Low power Pulse injection
Beam transport commissioned
Beam transport – riser
Switchyard
Beam transport pits
Beam Transport
Pulse commissioning
Focus on the commissioning of the beam transport for EA1
The probe commissioning timescales are still dependant on arrival of laser system and installation

## Slide 9
Experimental Area 1
Diagnostics
Focussing Chamber
Interaction chamber
EA1 ready for source commissioning experiments
Oct 25
Feb 25
March 25
April 25
July 25
May 25
June 25
Aug 25
Sept 25
Optic Installation & Initial alignment
Full Power Commissioning
Low Power commissioning
Nov 25
The timescales are indicative at this stage pending progress made on installation
The probe commissioning timescales are still dependant on arrival of laser system and installation
Electron beamline

## Slide 10
Commissioning has progressed well in PUMP and Front End
Commissioning activities currently in laser areas and progressing well
Key item in the critical path is the delivery of gratings
Looking a coordination of commissioning activities and installation in the experimental areas in the coming months
Summary

## Slide 11
Thank You