## Slide 1
ITRF/LhARA Review Session
24-month review
Hywel Owen (for collaboration)
3rd September 2024
Notes: The abstract pattern can be removed or repositioned if required. Be careful to ‘Send to Back’ so that it does not obscure any important information.

## Slide 2: Where are we?
6-month review
Re-examine baseline
12-month review
Progress major work, outline engineering assessment
18-month review
Establish CDR design, engineering integration
24 months
CDR

## Slide 3: Major Milestones Summary
Major Milestones Summary (key project stages and major deliverables) |  |  |  |  | 
Ref | Milestone Description | Baseline | Forecast | Variance | Comments
M2 | Refined scope, specifications, defined parameters and schematic diagram of facility equipment complete (6 month design review). | 23/03/23 | 21/03/23 | -3 | Complete
M4 | ITRF Baseline designs complete (12 month design review) | 21/09/23 | 20/09/23 | -2 | Complete
M11 | Refined ITRF specifications & designs (18 month design review) | 21/03/24 | 26/04/24 | 27 | Complete
M12 | Start ITRF CDR write up (21 month design meeting) | 20/06/24 | 20/06/24 | 1 | Complete
M18 | ITRF CDR Publication | 23/09/24 | 23/09/24 | 1 | 
M19 | ITRF CDR phase complete | 30/09/24 | 30/09/24 | 1 | 
24 Month review meeting September 2024 - Belfast

## Slide 4: Milestones
Minor Milestones Summary (green means finished) |  |  |  |  | 
M3 | Validate LhARA plasma simulations with existing Swansea experimental set-up (LhARA M3.1) | 03/04/23 | 14/06/24 | 315 | 
M5 | Prediction of optimised LhARA proton source parameters for 100+ TW laser systems based on hydrodynamic and kinetic simulations complete (LhARA M2.1). | 02/10/23 | 02/05/24 | 154 | 
M6 | Preliminary design of LhARA MA RF cavity, FFA magnet, diagnostic system, control & feedback systems complete. | 28/03/24 | 28/03/24 | 1 | 
M7 | Preliminary design study of LhARA Building concept design, bulk shielding assessment, mechanical systems integration support concepts, vacuum concepts, power consumption & cooling requirements complete. | 28/03/24 | 28/03/24 | 1 | 
M8 | First LhARA ion source simulations and experiment on SCAPA completed (LhARA M2.2) | 01/04/24 | 14/06/24 | 75 | 
M9 | Progress report of LhARA large diameter plasma experiments and simulations (LhARA M3.2) | 01/04/24 | 14/06/24 | 98 | 
M10 | Geant4 simulations of beam energy deposition profile (LhARA M4.1) | 01/04/24 | 01/04/24 | 1 | 
M13 | Finalise Conceptual Design iterations (All LhARA WP6 systems) complete | 24/07/24 | 24/07/24 | 1 | 
M14 | Next generation plasma lens test bench design (LhARA M3.3) | 30/08/24 | 30/08/24 | 1 | 
M15 | Acoustic sensor array design complete (LhARA M4.2) | 30/08/24 | 30/08/24 | 1 | 
M16 | Automated cell dish handling and environmental system design complete (LhARA M5.1), End-station user-community consultation complete (LhARA M5.2), End-station component testing at Birmingham complete (LhARA M5.3), kG,y/s tests at Birmingham complete (LhARA M5.7). | 30/08/24 | 30/08/24 | 1 | 
M17 | Specification of LhARA beam monitoring technology complete (LhARA M5.5) | 30/08/24 | 30/08/24 | 1 | 

## Slide 5: CDR Preparation
Content and deadlines
Author list
Institute acknowledgements – logos etc.
Printing, distribution and publicity
Press releases