## Sheet1
WP Number | WP2
WP Name | Linear Accelerators
Task | Task Description | Who? | Existing Effort |  |  |  | Requested Effort |  |  |  | Existing Material |  |  |  | Requested Material
|  |  | FTE Years |  |  |  | FTE Years |  |  |  | kEUR |  |  |  | kEUR
|  |  | Y1 | Y2 | Y3 | Y4 | Y1 | Y2 | Y3 | Y4 | Y1 | Y2 | Y3 | Y4 | Y1 | Y2 | Y3 | Y4
1 | Management of Study, support for writing of reports, etc | ISIS | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Dissemination and Communication | ISIS | 0.1 | 0.1 | 0.1 | 0.1 | 0.25 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Gender dimension and equality assurance | Someone | 0.1 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4
5
Deliverables | bar: FTE Years Y1; FTE Years Y1; kEUR Y1; kEUR Y1
Month | Deliverable Description | bar: FTE Years Y1; FTE Years Y1; kEUR Y1; kEUR Y1
6 | Data Management Plan
24 | Mid-term Report
45 | Final Report
Milestones | bar: FTE Years Y1; FTE Years Y1; kEUR Y1; kEUR Y1
Month | Milestone Description | bar: FTE Years Y1; FTE Years Y1; kEUR Y1; kEUR Y1
3 | Kick-off Meeting
12 | Annual Meeting
24 | Annual Meeting
36 | Annual Meeting
48 | Annual Meeting