## Slide 1
Meredith Lee
Accelerator Division/Target Systems Department
9/20/2022
LBNF Horns and Challenges

## Slide 2: Agenda
Overview of LBNF Horns
Challenges
  Welding Horns B & C Inner Conductors
  Horns B & C Forgings
  Horns B & C Coatings
  Assembly in Flipping Fixture
Summary
Horn B system overview

## Slide 3: Overview of LBNF Horns
Three horn focusing system
  Horn A followed by Horn B and Horn C
Pulsed at 300 kA
Designed for 1.2 MW and upgradeable to 2.4 MW
Horn B is largest horn to be built at Fermilab
  15 ft. long and 40 in. diameter
  Horn C has same diameter as Horn B
Horn A
Horn B
Horn C

## Slide 4: Overview of LBNF Horns
Prototype Horn A currently in fabrication
Outer conductor machined and surveyed
  To be hardcoat anodized soon
Inner conductor successfully welded in February
  X-Rayed to NAS 1514 Class 1 on both welds
  Straightened to within 0.020” TIR requirement
All supporting parts ordered and received
Horns B & C in final design stages
Prototype Horn A Outer Conductor

## Slide 5: Challenges
NuMI and BNB horn experience invaluable for LBNF
Several anticipated fabrication and assembly challenges
  Differences in design from NuMI
Large size creates fabrication and assembly challenges
  Many vendors cannot accommodate
  Space/storage constraints
  New assembly procedures with no NuMI/BnB precedent

## Slide 6: Challenges – Welding Horns B and C Inner Conductors
Horn B and C inner conductors have comparatively large diameter welds
  Horn A: 3.380”, 3.780” diameters
  Largest NuMI Horn 2 weld: 21.343”
Horn C Weld Diameters and Locations
Horn B Weld Diameters and Locations

## Slide 7: Challenges – Welding Horns B and C Inner Conductors
CNC TIG welding machine
  Program weld routines for precise control of welding parameters
    Current, arc voltage, wire feed rate, etc.
Order of operations for each horn weld:
  1. Welding over previous sample weld/multi-ring to test routine
  2. Weld sample part
  3. Modify routine and weld new sample
  4. Iterate between steps 2 and 3
    100% penetration weld
    Acceptable crown on weld surface
NuMI Horn 2 inner conductor on welding machine

## Slide 8: Challenges – Welding Horns B and C Inner Conductors
Four sample welds planned for each horn diameter
  Typically do up to 6 sample welds for NuMI and LBNF Horn A
Tack welds needed for larger welds (> 8” diameter)
  Ensure parts do not open up during welding
  Tack welds should have small crown and not produce underbead
  Can only test effectiveness on samples
Weld sample reusable parts approach

## Slide 9: Challenges – Welding Horns B and C Inner Conductors
Welding second Horn C weld at an angle
  Only experience doing this for BNB horn
Need to extend welding machine rails to accommodate Horn B length
Welding machine planned rail extension
Typical torch orientation
Torch rotated 16.8
Horn C inner conductor

## Slide 10: Challenges – Horns B and C Forgings
Horn B and C forgings are large and numerous
  Total of 24 horn and weld sample forgings
Expensive and long lead time
  Estimated cost: $750k for horn forgings
  Lead time based on Horn A experience: 5 months (only 3 forgings)
Only one vendor qualified for this job
  Excellent work for NuMI, BNB, and prototype Horn A
  Procuring all at once requires significant accommodation from vendor
Machining vendor options also limited
Horn A outer conductor forging
Notes: 12 weld sample forgings, 12 horn forgings

## Slide 11: Challenges – Horns B and C Coatings
Anodizing and nickel plating Horns B and C conductors
Large tank size needed
  Nickel plating: 16 ft length, < 58” width
  Anodizing: 16 ft x 5 ft x 5 ft
FNAL planning to build and supply tank to vendor
Fixture designs will need to be more contained within volume of horn than fixtures for previous horns
  Minimize tank size
Horn B nickel plating fixture concept

## Slide 12: Challenges – Assembly in Flipping Fixture
Flipping fixture rotates horn outer conductor for inner and outer conductor mating
Flipping fixture and Horn B use up nearly all available hook height
  32 ft minimum required
  ~35 ft hook height
6” clearance between conductors
30.9 ft
Initial orientation of Horn B OC in fixture
Inner conductor lowered into outer conductor

## Slide 13: Challenge – Assembly in Flipping Fixture
Must raise stands’ inner telescoping beams midway through assembly
  Allows for rotation of conductors back to horizontal
Raise both beams equally without binding
Install connecting plate and ceramic ring
16.2 ft
2.4 ft
Raising stand height for ceramic ring and connecting plate installation

## Slide 14: Summary
Fabricating Horns B & C pose the most challenges
Dependent on one vendor for forgings
Little margin for error for weld routine creation for inner conductor
Nickel plating and anodizing fixtures required to take up minimum volume
Assembly in flipping fixture requires challenging stand adjustment with conductors installed

## Slide 15: Backup

## Slide 16: Horn C Weld