## Specification
Parameter | Recent Spec (After TDR) |  | 10Hz Upgrade1,2 | 1 TeV CoM Spec 2 |  |  | Notes | Ref: | 1 CERN-ESU-004, Physics Briefing Book Input for the European Strategy for Particle Physics Update 2020, p168
Beam Energy (GeV) e- | 125 |  |  | 500 |  |  |  |  | 2 ILC250 accelerator, Shin Michizonono for US Snowmass AF-EF-meeting, June 2020, p6
Crossing Angle (mrad) | 14
Installation site (m from IP) | 14
RF Repetition Rate (Hz) | 5 |  | 10 | 4
number of bunches | 1312 |  | 2625 | 2450 |  |  | Updated by Yokoya-san 19/5
Bunch Train Length (ms) | 726.848 |  | 960.75 | 896.7 |  |  | Updated by Yokoya-san 19/5
Bunch Spacing (ns) | 554 |  | 366
Beam current (mA) | 5.8 |  | 8.75 | 7.6
Operating Temp (K) | 2 ?
Cryomodule installation length (m) | 3.8
Horizontal beam-pipe separation (m) | 0.197
Cavity Frequency (GHz) | 3.9 | 2.6 | 1.3 | 3.9 | 2.6 | 1.3
Total Kick Voltage (MV) | 0.615 | 0.923 | 1.845 | 2.5 | 3.7 | 7.4
Amplitude regulation/cavity (% rms) | 3.5 (for 2% luminosity drop) | [5 empty] | What is the stability anticipated for the applied kick voltage - Okugi-san 25/5
Relative RF Phase Jitter (deg rms) | 0.069
Timing Jitter (fs rms) | 49 (for 2% luminosity drop) | [5 empty] | Cavity-cavity jitter (rms) at arrival time, need to quantify re: frequency contributon, likely continuous?
Missing Parameters
Beam-cavity jitter (fs rms) | [6 empty] | What tolerance is anticipated - Not so tight - Okugi-san 25/5
Longitudinal impedance threshold (Ohm) | [6 empty] | Clarify approach to define threshold - Not so tight, need time distribution of wakefield - Okugi-san 25/5
Trasverse impedance threshold (Ohm/m)
Cavity alignment tolerance (x, y) (mm) | [6 empty] | Likely to be cavity specific - strongly depend on cavity field distribution - Okugi-san 25/5
Cavity field rotation tolerance/cavity (mrad rms) | 5.2 (for 2% luminosity drop) | [5 empty] | Okugi-san 25/5
Beam tilt tolerance (H and V) (mrad rms and urad rms) | 0.35, 7.4 (for 2% luminosity drop) | [5 empty] | Okugi-san 25/5
Minimum beam aperture size (mm) | 20 (same as FD magnets) | [5 empty] | Clarify expectation re:photon load anticipated - Okugi-san 25/5
Qext | [6 empty] | Beam-loading expected to be low - BDS team
Cavity bandwidth (Hz) | [6 empty] | Will be cavity specific
Input power (kW) | [6 empty] | Will be cavity specific
Cavity dynamic load (W) | [6 empty] | Will be cavity specific
Cryomodule static load (W) | [6 empty] | Will be cavity specific
Cavity aperture (H and V) (mm) | [6 empty] | Any constraints expected - BDS team - same as Row27?
Beam size at CC location (X, Y,Z) (mm,um,um) | 0.97, 66, 300 | [5 empty] | What collision volumes are anticipated - Okugi-san 25/5
Beta function at CC location (X, Y) (m,m) | 23200, 15400 | [5 empty] | Okugi-san 28/6
Microphonic effects, cryogenics? | [6 empty] | Are there any driving implications, likely to be cavity specific?
Active positioning expected, tolerance (X,Y) - 2mm indicated? | [6 empty] | Any guidance on this for CM development?
Multipole effects for CC (May take some time if not already available) | [6 empty] | Any other BDS specific impact - BDS team

## CC Development Plan
Activity | R&D Plan | Tmescale | [15 empty] | When?
|  | 2021 |  |  |  | 2022 (Yr 1) |  |  |  | 2023 (Yr 2) |  |  |  | 2024 (Yr 3)
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Set CC specifications | T0 + 3m | [16 empty] | 2021-06-24 | bar: 2021 Q2
Bare cavity EM design parameters | bar: 2021 Q3 to 2022 (Yr 1) Q2
Hom damped cavity parameters | bar: 2021 Q3 to 2022 (Yr 1) Q2
HOM coupler development | bar: 2021 Q3 to 2022 (Yr 1) Q2
Mechanical design | bar: 2021 Q4 to 2022 (Yr 1) Q2
Workshop review of various design options (cavity, HOMs, couplers) | T0 + 9m | [16 empty] | 2021-12-07 | bar: 2021 Q4
Multipacting assessment | bar: 2022 (Yr 1) Q1 to 2022 (Yr 1) Q2
Tuning solution and pressure analysis | bar: 2022 (Yr 1) Q1 to 2022 (Yr 1) Q2
Decision 1 - cavity shape, HOMs, couplers, multipacting, tuning, pressure stability, fabrication | T0 + 18m | [16 empty] | 2022-09-24 | bar: 2022 (Yr 1) Q3
Decision 1 (EM Design)
Decision 2 (Protototye)

## R&D Plan
| Milestone | Activity | When? | Duration (Months)? | Who? | Assumptions
| MS-0 | Set CC design specification | T0 + 3m | 3 | All CC groups, plus BDS/MDI/SRF input | What do we set as T0 (23/3)?
| MS-1 | Cavity EM design optimisation | T0 + 18m | 12 | All CC groups
| MS-2 | Coupler EM design optimisation (i.e. LOM, SOM and HOM) | T0 + 18m | 12 | All CC groups
Pre-Lab Phase | MS-3 | Dressed cavity mechanical design with tuner (concept) | T0 + 18m | 6 | All CC groups
| MS-4 | Prelim cavity down-selection process (2off) - Agreed | T0 + 18m | Decision 1 | All CC groups, plus BDS/MDI/SRF input, plus external reviewers
| MS-5 | Input coupler design and prototype validation | T0 + 36m | 24
| MS-6 | High power validation of prototype cavity? | T0 + 36m | 18
| MS-7 | Integrated 'dressed' cavity optimisation | T0 + 36m | 3
| MS-8 | Final Cavity down-selection (choose final solution)? Include input coupler Agreed | T0 + 36m | Decision 2
| MS-9 | Preliminary Crab CM design - confirm integration with beam-line specification | T0 + 48m | 24
| MS-10 | Final CM engineering design prior to production | T0 + 60m | 12 | Engineering Design Report to be completed
| MS-11 | CM assembly design | T0 + 60m | 6
| MS-12 | CM assembly tooling development | T0 + 60m | 6
| MS-13 | Design of CC pCM transport cage and shock damper | T0 + 66m | 6
| MS-14 | CC production, including cavities w/He tank + mag. shield for CM, high-pressure gas regulation, EP/HT/Clean work, including VT | T0 + 78m | 18
| MS-15 | Coupler production including preparation/RF processing readiness (excluding klystron, baking furnace, clean room) | T0 + 78m | 12
| MS-16 | CM production including High-pressure-gas formality, vacuum vessel, cold-mass (cavity-string, coupler/tuner, SCM, etc.) | T0 + 78m | 18
| MS-17 | Manufacture of CC pCM transport cage and shock damper system | T0 + 78m | 12
| MS-18 | Prototype CM (pCM) assembly | T0 + 84m | 18
| MS-19 | Acceptance verification of integrated CM | T0 + 85m | 1
| MS-20 | High power test of prototype CM | T0 + 91m | 6
| MS-21 | RF synchronisation of integrated 2-cavity CM cavities | T0 + 94m | 3
| MS-22 | Transportation validation (ship trans-atlantic and retest) | T0 + 100m | 6
Clarification needed:
Infratsruture, how incorporate (funding and staffing resource)? May need some indications from collaborators (even small expectations can be clarified)
Engineering design report during Pre-Lab, conceptual design, assign resources, include in WBS (resources to clarify)