## Slide 1
EPAC ISTAC
Technical Report
Pump Laser
Jonathan Phillips
30th November / 1st December 2022
Notes: The abstract pattern can be removed or repositioned if required. Be careful to ‘Send to Back’ so that it does not obscure any important information.

## Slide 2: Pump laser layout
Layout of the EPAC Pump Laser and Rack Rooms
Front End
120 J Amplifier
Pump Room
Rack Room
10J Amplifier
Pump Laser Parameter | Design requirement
Pulse energy | 200 J with pump A & B Day 1 = 120 J with pump A only
Pulse duration FWHM | 15 ns FWHM
Central wavelength | 1030 nm
Repetition rate | 1 Hz and 10 Hz
Notes: Add slide on FE with pulse shapes?

## Slide 3
Front End Pre-build
Pre-amplifier 1
Pre-amplifier 2
Output to 10 J
Built and commissioned in advance
  Fibre seed installed
  Pre-amplifier 1 installed
  Pre-amplifier 2 installed
  Opto-mechanics and optics delivered
Software Development
  Fibre seed – software complete
  Pulse shaping software – to be tested
  Pre-amplifier 1 – software complete
  Pre-amplifier 2 – software complete

## Slide 4
Output of Front End
Site Acceptance Test
Output Energy Specification 100 mJ
Measured Output energy 100 mJ for 6 + Hours
Output polarization Specification 20 dB
Measured Polarisation extinction ratio (PER) >20.3 dB

## Slide 5
10 J Amplifier Progress
  All major optics and opto-mechanics delivered
  10 J Cryostat FAT and delivered
  Cryo full loop (inc amp head) tested in Cryo manufactures factory
  Pump diodes FAT completed
  Debris shield designed
  Support structure designed and ordered
Notes: Add image of amp head?

## Slide 6
10 J Pumps FAT Complete
Beam profile of Module A
10 Pump modules
Successful completion of FAT
Output energy per Pump 35 J @10 Hz, 1.2 ms
Delivery in December 2022
Installation and SAT in the EPAC Pump room in January 2023

## Slide 7
Installation in EPAC
  10 J Cryo
  Fully commissioned at manufacturing company
  Leak tested with 10 J Amplifier Head
  Moved to EPAC building
  10 J Cryo cooling system to be commissioned in
  January 2023 in the EPAC building
10 J cryostat
(GRE)
Location of amplifier head and support structure
(CLF design)

## Slide 8
120 J Amplifier
Output beam
Input structure design completed
Output structure designed completed
Debris shields designed completed
General enclosure design to be finished
Polarisation insensitive diagnostics

## Slide 9: Update on 120 J Pumps
  120 J Pump diode
  All optics for pump diodes have been received
  Pump engine 1 and 2 built
  1 Year late, headroom for delay as currently not impacting commissioning plans
  FAT due for 3rd week of January 2023
  Software Interface / Protocols still to be tested

## Slide 10
Installation in EPAC
  120 J cryo-cooling systems
  Fully commissioned at manufacturing company
  Leak tested with 120 J Amplifier head
  Moved to EPAC building
  120 J Cryo cooling system to be commissioned this January 2023 in the EPAC building

## Slide 11
Status of Services
On track for Dec 2022
Rack room
10 J Pump and server
120 J Pump and server
PA1 and PA2 racks
Cryostat racks
Vacuum pumps
Pump room
Trunking for services
Distribution control systems
Power
Data
Water
Gas
Turbos backing pump in lab
LN2 feed and exhaust installed
Laser Interlocks

## Slide 12
Provision included in services design, space in 209, TJ-HJ-2 beam transport and wall apertures for delivery to Ti:S Room (202)
Future provision; two 120J sections

## Slide 13
Status
  D100-X at HiLASE has increased energy to 145 J at 10 Hz
  Operated stably @100 J at 10 Hz for extended periods
  Deplorisation: extensive characterisation and modelling, concepts for mitigation
  Reduced depolarization losses to 8%
  New results indicate that 3% depolarization can be achieved
Depolarisation
Input polarisation optimised,
nominal pumping parameters
Depolarisation Loss = 7.9%

## Slide 14
Current status of EPAC Pump Room
Current installation
FE Optics and table
Service trays
10 J Cryo and 120 J Cryo
10 and 120 J Cryo Amplifier heads
Cable racks
Commissioning starts in March 2023

## Slide 15
@STFC_Matters
Science and Technology Facilities Council
Science and Technology Facilities Council
Thank you
Extreme Photonics Applications Centre (EPAC)
Notes: The abstract pattern can be removed or repositioned if required. Be careful to ‘Send to Back’ so that it does not obscure any important information.