## Questions
1272-pa1-pm-rev-0001 | v0.1
List of technical questions to address at ITRF/LhARA 18 month design review
Stage 1
| Question | Resolution | Comments
* | Definition of 'standard' source for proton emission | (in progress - needs code and write-up)
How are carbon ions to be generated?
| Is helium needed? If so, how will it be delivered? |  | Is this a red herring? Narrative needed in CDR
* | Importance of space charge on losses and emittance |  | (from LhARA-Gov-PMB-2022-02) | Included in present update to baseline
| Vacuum pressure levels between source and Gabor lens |  | can the vacuum pressure gradient and beaming be tolerated?
| What is the roadmap for the delivery of a suitable Gabor lens? |  | (from LhARA-Gov-PMB-2022-02)
Stage 2
| Question | Resolution | Comments
* | Choice of cavity technology for FFA - MA or ferrite? |  | 1272-pa1-pm-rpt-0008 lists parameters incl 4 kV and frequency swing
Determine budget length for FFA cavity
FFA optics - need for tuneability?
* | FFA magnet design - does it need to be flat? |  | Consequences of having a combined-function dipole? | Lose slow extraction, lose multiple species, lose risk mitigation of fied shaping
FFA magnet design - benefits of moving to a smaller beam aperture?
* | Is the total powering budget acceptable? |  | Place in correct context of analogous projects
How will spatial fractionation be delivered?
* | Comparison of FFA with synchrotron (and RCS) |  | (from LhARA-Gov-Rev-2022-01) | 100 Hz not possible with synchrotron, hence FFA only option at 100 Hz
* | Complexity of injection line into FFA - is it feasible?
| Is slow extraction feasible from the FFA? |  | Conclusions from Taylor's paper?
| Injection position into FFA (and extraction) |  | Present location appears to be the best (injection angle, location of extraction point wrt to facility layout etc.)
| Can we use a degrader to adjust Stage 2 energy? |  | Too much beam intensity loss, needs dedicated clean-up section, better to do it magnetically. What is the eventual specification for repetition rate and does degrader limit it?
| Can FFA trim coil terminations come out at the side? |  | Likely yes, but coil manufacturing is anyway going to be complex.
| FFA trim coils can be powered in parallel (top/bottom)? |  | Likely yes, and series around the ring.
PoP
| Question | Resolution | Comments
What is the key experimental outcome that is aimed for?
What is the defined experimental arrangement?
What is the temperature control required in the sample environment?
What are the requirements for the PoP delivery beamline?
| Will individual calibrated dishes (i.e. their thicknesses) be used | Yes, for each type of sample | CTM on beamline
User Programme
| Requirement for co-located animal house? |  | Regulatory issues
| User model for exploitation of Stage 2 in-vivo work? |  | Percentage of time and experimental outcome; risk within project?
| Gantry vs animal rotation? |  | (from LhARA-Gov-PMB-2022-02) red herring?
| Ensure access to experimental reference beams |  | (from LhARA-Gov-PMB-2022-02)
| Definition of minimum and optimum requirements |  | (from LhARA-Gov-PMB-2022-02) | Addressed by user consultation but needs to be in CDR

## Short Set
1272-pa1-pm-rev-0001 | v0.3
List of technical questions to address at ITRF/LhARA 18 month design review
Stage 1
| Question | Resolution | Comments
* | Definition of 'standard' source for proton emission | (in progress - needs code and write-up)
* | Importance of space charge on losses and emittance |  | (from LhARA-Gov-PMB-2022-02) | Included in present update to baseline
Stage 2
| Question | Resolution | Comments
* | Choice of cavity technology for FFA - MA or ferrite? |  | 1272-pa1-pm-rpt-0008 lists parameters incl 4 kV and frequency swing
* | FFA magnet design - does it need to be flat? |  | Consequences of having a combined-function dipole? | Lose slow extraction, lose multiple species, lose risk mitigation of fied shaping
* | Is the total powering budget acceptable? |  | Place in correct context of analogous projects
* | Comparison of FFA with synchrotron (and RCS) |  | (from LhARA-Gov-Rev-2022-01) | 100 Hz not possible with synchrotron, hence FFA only option at 100 Hz
* | Complexity of injection line into FFA - is it feasible?
User Programme
| Requirement for co-located animal house? |  | Regulatory issues
| User model for exploitation of Stage 2 in-vivo work? |  | Percentage of time and experimental outcome; risk within project?
| Gantry vs animal rotation? |  | (from LhARA-Gov-PMB-2022-02) red herring?
| Ensure access to experimental reference beams |  | (from LhARA-Gov-PMB-2022-02)
| Definition of minimum and optimum requirements |  | (from LhARA-Gov-PMB-2022-02) | Addressed by user consultation but needs to be in CDR